## README
Item | Detail
Purpose | Delivery blueprint for the Stall Watch trial: dependency-ordered backlog, sprint plan and delivery artifacts.
How to use | Work stories in ID order within a sprint. A story is Ready when all Blocked By stories are Done. Tabs 4 to 8 are the plan; 9 to 15 are reference; 16 is the Jira import.
Status legend | Draft (waiting on a prerequisite) > Ready > In Progress > Blocked > Code Review > QA Testing > UAT > Done. Draft flips to Ready when predecessors are Done.
Priority legend | P0 critical path (Highest), P1 high, P2 medium, P3 nice-to-have (Low).
Points | 1 point is about 6 minutes of focused work (calibrated to the brief's 7 hour budget: 2 sessions x ~35 points).
Waves | Wave 1: Foundations & Identity ¦ Wave 2: Core Data + Guardrails ¦ Wave 3: Core Value (stall rule + screens) ¦ Wave 4: Automation (detector, schedule, console) ¦ Wave 5: Docs, Part 3 & Submission
Workstreams | WS-DB: Database, RLS and migrations ¦ WS-WEB: Next.js app and screens ¦ WS-OPS: Repo, CI/CD, docs and submission
Ticket references | SW-nnn means US-nnn in this workbook (Jira assigns its own keys on import; the blueprint number is kept in the description and a us-nnn label).
Conventions | Branch: <type>/sw-<nnn>/<short-title>. Commits: Conventional Commits, e.g. feat(stall): record every detector run (SW-024). Merge commit or rebase, never squash.
Non-negotiables | RLS enabled and forced everywhere; idempotent detector; failed runs recorded as failed; no service-role key; no secrets in git.
Totals | 8 epics, 24 features, 36 stories, 69 points; Sprint 1 = 34, Sprint 2 = 35.

## Project Overview
Section | Detail
Summary | A small multi-tenant web app where home builders pick finishes for projects, and a scheduled detector alerts the right admins in the app when a project goes quiet.
Context | Take-home trial for Reverie3D (Automation Engineer). The app is a vehicle; graded on database security, automation quality and engineering habits.
Objectives | 1) Prove tenant isolation in the database. 2) Ship an idempotent, secured, observable stall detector. 3) Show professional habits (design note first, PRs, CI, migrations, ledger). 4) Write the Part 3 next-step note.
Target users | Ana (Builder A admin), Mia (Builder A member), Bruno (Builder B admin), Sam (Reverie3D staff); plus two reviewers.
KPIs | First run on seed flags exactly 3 projects (Lot 12, Unit 4B, Unit 7C); 0 duplicate alerts on re-run; 0 cross-tenant rows readable or writable; CI green on main; total time within 6 to 8 hours.
Constraints | Free tiers only; public repo; no service-role key; no email/SMS; one design note committed before code; database rebuildable from migrations alone.
Assumptions | See Gaps & Assumptions tab (G-01 to G-20).
Top risks | Missed policy or with check; failure log lost in rollback; definer function left callable; time overrun. See Risk Register.
Cut order if short | Bonus build, then UI polish, then non-rule docs. Never RLS, idempotency, or failure logging; say what you cut in DESIGN.md.

## Product Roadmap
Phase | Scope | Epics | Waves | Release target | Priority | Dependencies
MVP / Phase 1: Foundation | Repo, deploy, identity, builder schema, history, seed, stall views, login | EP-01, EP-02, EP-03, EP-04, part of EP-05 | 1, 2, 3 | End of Session 1 (Wed 21 Oct 2026, suggested) | P0 | None
Phase 2: Detector | Screens finished, detector engine, schedule, console, verification | rest of EP-05, EP-06 | 3, 4 | Mid Session 2 | P0 | Phase 1
Delivery | CI db job, ledger, SETUP.md, final DESIGN.md, verification, submission | EP-07 | 5 | End of Session 2 (Thu 22 Oct 2026, suggested) | P0 | Phase 2
Phase 3: Next step | Write-up (required) and late-change alert (bonus, only if solid) | EP-08 | 5 | End of Session 2 | P1 / P3 | Phase 2

## Epic Backlog
Epic ID | Name | Description | Business Value | Priority | Dependencies | Acceptance Criteria | Points | Status
EP-01 | Project Foundation & Delivery Pipeline | Repo, design note, platforms, deploy and CI so every later change ships through PRs. | Reviewers read git history and CI; this epic proves the habits graded in the brief. | P0 | None | Design note committed first; live URL; CI green; no secrets in git. | 7 | Ready
EP-02 | Identity, Tenancy & RLS Core | private schema, identity tables, auth mirror, RLS helpers and identity policies. | Tenant isolation starts with identity; every later policy calls these helpers. | P0 | EP-01 | Helpers work for strangers (empty), RLS forced on identity tables, apps cannot write identity. | 8 | Draft
EP-03 | Builder Data Model & Isolation Proof | builder schema, composite foreign keys, RLS, alerts storage, seed, test users and isolation tests. | Builder A must never read or write Builder B data; the database is the wall. | P0 | EP-02 | Cross-tenant reads and writes fail in tests; seed loads unchanged. | 11 | Draft
EP-04 | Selection Activity History | Append-only history written by a definer trigger with database-computed actor_kind. | The stall rule needs trustworthy builder-vs-staff activity that clients cannot forge. | P0 | EP-03 | set/change/clear logged; actor_kind from membership; history append-only. | 3 | Draft
EP-05 | Builder & Staff Screens | Login, projects list with live stalled badge, project detail, alerts inbox. | Lets Ana, Mia, Bruno and Sam do the end-to-end story in a browser. | P0 | EP-03, EP-04 | Whole brief story works in a real browser as each persona. | 9 | Draft
EP-06 | Stall Detector & Alerts | Live stall rule, detector engine, run log, de-duplication, schedule, staff trigger, console and verification. | The business problem: notice quiet projects and tell the right admins in the app. | P0 | EP-03, EP-04 | 3 stalls on seed, zero duplicates on re-run, failures logged as failed, secured. | 18 | Draft
EP-07 | Documentation, Verification & Submission | Automated DB checks in CI, migration ledger, SETUP.md, final DESIGN.md, pre-submit verification and submission. | A stranger must rebuild the environment from the repo alone; submission has strict secrecy rules. | P0 | EP-06 | Fresh-project rebuild passes; checklist complete; two one-time secret links sent. | 9 | Draft
EP-08 | Part 3: What I'd Build Next | Written pick (required) and optional late-change alert build. | Shows product judgment; bonus only if Parts 1 and 2 are solid. | P1 | EP-06 | Write-up covers why/how/leave out; bonus built to Part 2 standard or skipped. | 4 | Draft

## Feature Backlog
Feature ID | Epic | Name | Description | Priority | Complexity | Dependencies | Points | Status
F-01.1 | EP-01 | Kickoff & Design Note | Estimate reply and design note committed before code. | P0 | S | None | 2 | Ready
F-01.2 | EP-01 | Repo & Platform Setup | Next.js scaffold and Supabase project/config. | P0 | M | US-002 | 3 | Draft
F-01.3 | EP-01 | Deploy & CI Pipeline | Vercel deploy with env per environment and CI checks. | P0 | M | US-003, US-004 | 2 | Draft
F-02.1 | EP-02 | Identity Schema | private schema, shared trigger, identity tables. | P0 | M | US-004 | 3 | Draft
F-02.2 | EP-02 | Auth Mirror & RLS Helpers | auth.users mirror and private helper functions. | P0 | M | US-008 | 3 | Draft
F-02.3 | EP-02 | Identity RLS | Forced RLS and read-only policies for identity tables. | P0 | M | US-010 | 2 | Draft
F-03.1 | EP-03 | Builder Schema & RLS | Builder tables, composite FKs, policies, grants, exposure. | P0 | L | US-011 | 6 | Draft
F-03.2 | EP-03 | Alerts Storage | Alerts table with recipient-only policies and column grant. | P0 | M | US-013 | 2 | Draft
F-03.3 | EP-03 | Seed, Users & Isolation Proof | Load seed, test users and cross-tenant attack tests. | P0 | M | US-009, US-013, US-014, US-015 | 3 | Draft
F-04.1 | EP-04 | Selection History | Definer trigger, actor_kind, append-only guard. | P0 | M | US-013 | 3 | Draft
F-05.1 | EP-05 | Auth Session & Login | SSR Supabase clients and /login. | P0 | S | US-005, US-016 | 2 | Draft
F-05.2 | EP-05 | Projects List | /projects with live stalled badge. | P0 | M | US-018, US-019 | 3 | Draft
F-05.3 | EP-05 | Project Detail | /projects/[id] selection editing. | P0 | M | US-015, US-019 | 2 | Draft
F-05.4 | EP-05 | Alerts Inbox | /alerts with mark as read. | P0 | S | US-014, US-019 | 2 | Draft
F-06.1 | EP-06 | Stall Rule | Live views implementing the stall rule. | P0 | M | US-015, US-016 | 3 | Draft
F-06.2 | EP-06 | Detector Engine | Run log, episodes, function with failure logging. | P0 | L | US-013, US-014, US-018 | 7 | Draft
F-06.3 | EP-06 | Scheduling & Staff Trigger | pg_cron job and staff-guarded run-now RPC. | P0 | M | US-024 | 3 | Draft
F-06.4 | EP-06 | Detector Console | /detector run history and Run now. | P0 | S | US-019, US-025 | 2 | Draft
F-06.5 | EP-06 | Detector Verification | Scenario tests: counts, idempotency, failure, overlap, auth. | P0 | M | US-024, US-025 | 3 | Draft
F-07.1 | EP-07 | Automated Checks | CI database job running seed and SQL tests. | P1 | M | US-006, US-015, US-028 | 2 | Draft
F-07.2 | EP-07 | Migration & Setup Docs | Ledger, headers, SETUP.md, final DESIGN.md. | P0 | M | US-026, US-027 | 4 | Draft
F-07.3 | EP-07 | Verification & Submission | Fresh rebuild, secret scan, advisors, secret links. | P0 | M | US-029, US-030, US-031, US-032, US-033 | 3 | Draft
F-08.1 | EP-08 | Next-Step Write-up | Required Part 3 write-up in DESIGN.md. | P1 | S | US-002 | 1 | Draft
F-08.2 | EP-08 | Late-Change Alert (bonus) | Trigger alerting staff on builder changes after revision. | P3 | M | US-024, US-028 | 3 | Draft

## Product Backlog
Story ID | Epic | Feature | Summary | User Story | Acceptance Criteria | Priority | Points | Wave | Workstream | Sprint | Dependencies | Status
US-001 | EP-01 | F-01.1 | Send time estimate and planned submit date | As the candidate, I want to reply to Reverie3D with my time estimate and planned submit date so that they can track my progress against it. | [ ] Reply is sent before any build work starts and states an estimate of about 7 hours. [ ] Reply names one specific planned submit date. [ ] A copy of the message is kept in docs/tickets/SW-001.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-OPS | 1 | None | Ready
US-002 | EP-01 | F-01.1 | Write and commit first DESIGN.md before any code | As the candidate, I want to a half-page DESIGN.md committed first so that reviewers can see decisions were made before code. | [ ] DESIGN.md starts with the two lines 'Candidate: <name>' and 'Hours spent: <n>'. [ ] It has Problem, Goals/non-goals, planned data and permissions, and decisions with rejected alternatives. [ ] Given the git log, when listing commits oldest first, then the DESIGN.md commit precedes every app and migration commit. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-OPS | 1 | None | Ready
US-003 | EP-01 | F-01.2 | Scaffold repo and Next.js app with conventions | As the candidate, I want to a Next.js App Router TypeScript app with lint and typecheck scripts so that every later change is checked the same way. | [ ] TypeScript strict mode; npm run lint, typecheck and build all pass on the empty app. [ ] .gitignore excludes .env* except .env.example, which lists NEXT_PUBLIC_SUPABASE_URL and NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY with a comment each and no values. [ ] README explains local run; work is on a branch merged via PR with Conventional Commits. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 1 | WS-OPS | 1 | US-002 | Draft
US-004 | EP-01 | F-01.2 | Create Supabase project, link CLI, set exposed schemas in config.toml | As the candidate, I want to a linked Supabase project and a committed config.toml so that the database can be rebuilt from the repo. | [ ] supabase link succeeds and supabase/config.toml is committed with api schemas listing public and builder. [ ] No schema object is created in the dashboard (settings only). [ ] Steps taken are noted for SETUP.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-OPS | 1 | US-003 | Draft
US-005 | EP-01 | F-01.3 | Deploy hello page to Vercel with per-environment variables | As the candidate, I want to a live URL with env vars set per environment so that reviewers can open the app and previews work. | [ ] Live URL serves the hello page from main. [ ] The two NEXT_PUBLIC variables exist in Production, Preview and Development; no service-role key is set anywhere. [ ] A PR opened against main produces a Vercel preview deployment. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-OPS | 1 | US-003, US-004 | Draft
US-006 | EP-01 | F-01.3 | CI: lint, typecheck and build on every PR | As the candidate, I want to a GitHub Actions workflow so that a red PR is never merged. | [ ] Workflow runs lint, typecheck and build on pull_request and on push to main. [ ] Given a deliberate lint error, when the PR runs, then CI fails (shown once, then reverted). [ ] CI uses no secrets. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-OPS | 1 | US-003 | Draft
US-007 | EP-02 | F-02.1 | Private schema and shared updated_at / lock_version trigger | As the candidate, I want to a private schema and one shared trigger function so that all mutable tables stamp updated_at and bump lock_version consistently. | [ ] Schema private exists and is not in the exposed API schemas. [ ] private.touch_updated_at() sets updated_at = now() and lock_version = lock_version + 1 on update. [ ] Migration has WHY/WHAT/ROLLBACK header and a MIGRATIONS.md row. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-DB | 1 | US-004 | Draft
US-008 | EP-02 | F-02.1 | Identity tables: orgs, users, memberships | As the candidate, I want to orgs, users and memberships with strict constraints so that tenancy and staff status come from data the client cannot influence. | [ ] orgs.org_type is text with check in ('staff','builder'); memberships.role check in ('admin','member'). [ ] unique (user_id, org_id) on memberships and unique email on users; uuid default gen_random_uuid() keys; created_at, updated_at, lock_version present. [ ] public tables do not reference builder tables. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 1 | WS-DB | 1 | US-007 | Draft
US-009 | EP-02 | F-02.2 | Auth-mirror trigger copies auth.users into public.users | As the candidate, I want to new Supabase Auth users mirrored into public.users so that link-test-users.sql can find them and the app has a users table. | [ ] Given a user created in the dashboard, when the insert commits, then public.users has the same id and email. [ ] Trigger function is security definer with search_path = '' and execute revoked from public, anon and authenticated. [ ] Existing auth users are backfilled by the migration. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 1 | WS-DB | 1 | US-008 | Draft
US-010 | EP-02 | F-02.2 | RLS helper functions in private | As the candidate, I want to private.current_user_org_ids() and private.is_staff() so that every policy uses one audited predicate. | [ ] current_user_org_ids() returns uuid[] of the caller's orgs and an empty array for a user with no membership. [ ] is_staff() is true only for members of an org whose org_type is 'staff'. [ ] Both are security definer, search_path = '', execute revoked from public and anon, granted to authenticated; usage on private granted; the header explains why they work despite forced RLS (postgres BYPASSRLS). Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 1 | WS-DB | 1 | US-008 | Draft
US-011 | EP-02 | F-02.3 | Identity RLS: enable, force, read-only policies | As a reviewer, I want to forced RLS on identity tables with read-only policies so that apps can never write orgs, memberships or users directly. | [ ] ENABLE and FORCE ROW LEVEL SECURITY on orgs, users, memberships with p_<table>_select policies. [ ] INSERT, UPDATE, DELETE privileges revoked from authenticated and anon. [ ] Given a signed-in user with no membership, when selecting from orgs, then zero rows. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 1 | WS-DB | 1 | US-010 | Draft
US-012 | EP-03 | F-03.1 | Builder schema and core tables with composite foreign keys | As the candidate, I want to projects, slots, selections and history in schema builder so that child rows cannot disagree with their parent org. | [ ] Tables: projects, project_slots, selections, selection_history; statuses are text + check; unique (id, org_id) on projects and slots. [ ] Composite FKs: slots (project_id, org_id), selections (slot_id, org_id), history (slot_id, org_id); selections.slot_id unique; history.product_name nullable. [ ] Check: status = 'selection_phase' requires selection_phase_started_at; mutable tables carry created_at, updated_at, lock_version with the shared trigger. [ ] Given a selection insert whose org_id differs from its slot's org_id, then a foreign key violation is raised. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 2 | WS-DB | 1 | US-011 | Draft
US-013 | EP-03 | F-03.1 | Builder RLS policies, grants and API exposure | As a Builder A admin, I want to policies scoped to my org so that I can only see and change my own builder's data. | [ ] ENABLE and FORCE RLS on every builder table; policies named p_<table>_<command> use org_id = any (private.current_user_org_ids()) or private.is_staff(). [ ] projects UPDATE is staff only; selections INSERT/UPDATE/DELETE use org-or-staff with check; slots and history have no write policy. [ ] grant usage on schema builder and table grants go to authenticated only; anon has none. [ ] builder is added to the hosted exposed schemas and recorded for SETUP.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 2 | WS-DB | 1 | US-012 | Draft
US-014 | EP-03 | F-03.2 | Alerts table with recipient-only policies and column grant | As an admin, I want to alerts only I can read and mark read so that other users and staff cannot see my alerts. | [ ] builder.alerts has org_id, user_id, project_id, kind, message, read_at, created_at with composite FK (project_id, org_id). [ ] p_alerts_select and p_alerts_update use user_id = auth.uid(); UPDATE revoked then grant update (read_at) only; no insert or delete grants to authenticated. [ ] Given Ana updates message on her own alert, then permission denied; updating read_at succeeds. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 2 | WS-DB | 1 | US-013 | Draft
US-015 | EP-04 | F-04.1 | Selection history trigger with computed actor_kind | As a reviewer, I want to history written by a definer trigger so that builders cannot forge who made a change. | [ ] Insert on selections writes action 'set', update 'change', delete 'clear' (product_name null) with changed_by = auth.uid(). [ ] actor_kind is 'builder' when the caller is a member of the project's org, else 'staff'; with no auth.uid() it is 'staff'. [ ] Trigger function is security definer, search_path = '', execute revoked; UPDATE and DELETE on history are blocked. [ ] Migration header says the definer use is deliberate. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 2 | WS-DB | 1 | US-013 | Draft
US-016 | EP-03 | F-03.3 | Load seed.sql, create test users, link memberships | As the candidate, I want to provided sample data and four test users so that I can test every scenario. | [ ] seed.sql applies unchanged to the migrated database without error. [ ] Users staff@stallwatch.test, ana@builder-a.test, bruno@builder-b.test, mia@builder-a.test exist and link-test-users.sql runs clean twice. [ ] Memberships: staff admin of Reverie3D Studio, Ana admin A, Bruno admin B, Mia member A; no passwords are committed. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 2 | WS-DB | 1 | US-009, US-013, US-014 | Draft
US-017 | EP-03 | F-03.3 | Isolation tests and forced-RLS catalog check | As a reviewer, I want to SQL tests that attack Builder B as Builder A so that isolation is proven, not assumed. | [ ] Tests in supabase/tests/ impersonate users via request.jwt.claims. [ ] Given Ana, when selecting Builder B rows from projects, slots, selections, history and alerts, then zero rows; cross-org selection insert is rejected. [ ] A catalog query returns zero public/builder tables lacking enable and force RLS. [ ] Anon is denied on every table. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 2 | WS-DB | 1 | US-016, US-015 | Draft
US-018 | EP-06 | F-06.1 | Stall rule views (v_project_stall, v_projects) | As a staff user, I want to a live stall rule so that the badge is always current. | [ ] Views are security_invoker = true (reloptions checked) and set again after any create or replace. [ ] Given the seed, is_stalled is true for Lot 12, Unit 4B and Unit 7C and false for the other six projects. [ ] Quiet since = greatest(selection_phase_started_at, last builder history); staff activity is ignored (Unit 7C). [ ] Given Ana, then only Builder A rows are visible; v_projects exposes org_name, empty_slots, quiet_since, is_stalled. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 3 | WS-DB | 1 | US-016, US-015 | Draft
US-019 | EP-05 | F-05.1 | Supabase SSR clients, session refresh and /login | As a user, I want to to sign in with email and password so that I can reach my projects. | [ ] @supabase/ssr server and browser clients configured with the publishable key only; session refreshed in middleware/proxy. [ ] Given valid credentials, /login redirects to /projects; invalid credentials show a plain error. [ ] Given a signed-out visitor, /projects redirects to /login; no service-role key exists in code or Vercel. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 3 | WS-WEB | 1 | US-005, US-016 | Draft
US-020 | EP-05 | F-05.2 | /projects with live stalled badge | As a Builder A admin, I want to my org's projects with a stalled badge so that I know which ones need attention. | [ ] Builders see only their org's projects; staff see all with the org name. [ ] Each project shows empty slots, due date and a Stalled badge driven by v_projects. [ ] Given Ana makes one selection on Lot 12, when the page reloads, then the badge is gone. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 3 | WS-WEB | 2 | US-018, US-019 | Draft
US-021 | EP-05 | F-05.3 | /projects/[id] slots with set, change and clear | As a Builder A member, I want to to pick, change or clear a product per slot so that the project progresses. | [ ] Slots grouped by room show the current product with Set/Change and Clear. [ ] A builder write records history with actor_kind 'builder'; a staff write records 'staff'. [ ] Given Ana opens a Builder B project id, then not found or empty; no data leaks. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 3 | WS-WEB | 2 | US-019, US-015 | Draft
US-022 | EP-05 | F-05.4 | /alerts inbox with mark as read | As an admin, I want to my alerts newest first with mark as read so that I act on stalls. | [ ] Lists only the caller's alerts ordered by created_at desc; unread are visually distinct. [ ] Mark as read updates read_at only. [ ] Given Sam, then he sees only his own alerts, never Ana's. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 3 | WS-WEB | 2 | US-019, US-014 | Draft
US-023 | EP-06 | F-06.2 | Detector tables: stall_runs, stall_episodes, alerts.episode_id | As the candidate, I want to a run log and a de-duplication record so that re-runs and overlaps cannot duplicate alerts. | [ ] stall_runs: started_at, finished_at, trigger in (scheduled, manual), projects_flagged, alerts_created, status in (running, succeeded, failed), error_message. [ ] stall_episodes unique (project_id, quiet_since); alerts gets episode_id with unique (episode_id, user_id). [ ] Both tables have forced RLS with staff-only SELECT via private.is_staff() and no write grants to authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 4 | WS-DB | 2 | US-013, US-014 | Draft
US-024 | EP-06 | F-06.2 | private.run_stall_detector with failure logging and locking | As a Builder A admin, I want to an alert when my project stalls so that I act before the due date. | [ ] Given the seed, first run flags 3 projects and creates alerts: Ana 1, Bruno 2, Mia 0, staff 0. [ ] Given a second immediate run, zero new episodes and zero new alerts; run still logged as succeeded. [ ] Alert text matches: 'Lot 12 has had no builder activity for 7 days. 3 slots are still empty.' [ ] Given a forced error inside the work block, the run row is failed with error_message and no partial alerts remain. [ ] security definer, search_path = '', pg_advisory_xact_lock taken, execute revoked from public, anon and authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 5 | 4 | WS-DB | 2 | US-023, US-018 | Draft
US-025 | EP-06 | F-06.3 | Staff-guarded run-now RPC | As a staff user, I want to to run the detector on demand so that I can verify fixes immediately. | [ ] public.run_stall_detector_now() raises 42501 unless private.is_staff(); first lines of the body perform the check. [ ] Returns the run row; revoked from public and anon, granted to authenticated. [ ] Given Ana or anon, then forbidden; given Sam, a manual run is logged. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 4 | WS-DB | 2 | US-024 | Draft
US-026 | EP-06 | F-06.3 | pg_cron daily schedule | As a staff user, I want to the detector to run nightly without anyone pressing anything so that stalls are found automatically. | [ ] Extension pg_cron enabled; job stall-detector-daily calls private.run_stall_detector('scheduled') once a day. [ ] The cron.schedule command contains no secret; the migration is its own file with a NOT SELF-CONTAINED note. [ ] After forcing the job once, cron.job_run_details shows success and a scheduled stall_runs row exists. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 4 | WS-DB | 2 | US-024 | Draft
US-027 | EP-06 | F-06.4 | /detector run history and Run now | As a staff user, I want to run history and a Run now button so that I can answer 'did it run and did it work?'. | [ ] Table lists started, finished, trigger, projects flagged, status and error, newest first; failed runs show the error. [ ] Run now calls the RPC and refreshes with the new row. [ ] Given Ana opens /detector, then no data and the RPC is rejected (verified in the database, not just hidden in the UI). Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 4 | WS-WEB | 2 | US-025, US-019 | Draft
US-028 | EP-06 | F-06.5 | Detector scenario tests | As a reviewer, I want to scripted scenarios so that correctness and security are proven. | [ ] First-run counts, immediate re-run (0 new), new stall after builder activity plus backdating (1 new alert). [ ] Failure injection leaves a failed run with no partial alerts; two concurrent sessions create one set of alerts. [ ] Builder, anon and direct private-function calls are rejected; staff activity on Unit 7C leaves it stalled. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 3 | 4 | WS-DB | 2 | US-024, US-025 | Draft
US-029 | EP-07 | F-07.1 | CI database job | As a reviewer, I want to CI that rebuilds the DB and runs SQL tests so that regressions in security rules are caught automatically. | [ ] Job starts local Supabase, applies migrations, loads seed.sql, runs supabase/tests/*.sql. [ ] Any failed assertion fails the PR; forced-RLS catalog check included. [ ] Job is green on main. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P1 | 2 | 5 | WS-OPS | 2 | US-006, US-015, US-028 | Draft
US-030 | EP-07 | F-07.2 | MIGRATIONS.md ledger and header audit | As a reviewer, I want to one ledger row per migration and WHY/WHAT/ROLLBACK headers so that the schema history is explainable. | [ ] MIGRATIONS.md has one row per file with filename and what it did. [ ] Every migration has WHY, WHAT, ROLLBACK (and NOT SELF-CONTAINED where needed) and a YYYYMMDDHHMMSS_name.sql filename. [ ] No applied migration was edited after the fact. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 5 | WS-OPS | 2 | US-026 | Draft
US-031 | EP-07 | F-07.2 | SETUP.md for a teammate rebuilding from nothing | As a reviewer, I want to a literal setup guide so that I can rebuild on a fresh Supabase project. | [ ] Covers Supabase (create, link, db push, exposed schemas, pg_cron, other settings), order: migrations, seed, users, link script. [ ] Covers every Vercel env var with environments and browser exposure, CI contents, and the sandbox/production split. [ ] Followed literally on a scratch project it succeeds. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 5 | WS-OPS | 2 | US-026, US-027 | Draft
US-032 | EP-07 | F-07.2 | Finalize DESIGN.md | As a reviewer, I want to the final design note so that I can see decisions and trade-offs. | [ ] Detector section states where it runs, how it gets permission, what stops duplicates, and what was given up. [ ] 'Rules I bent' and 'What I cut' sections exist, listing any rule broken on purpose and why. [ ] The first two lines still read Candidate and Hours spent with an honest total; the note is 1 to 2 pages. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 5 | WS-OPS | 2 | US-031 | Draft
US-033 | EP-08 | F-08.1 | Part 3 write-up: what I'd build next | As a reviewer, I want to a reasoned next-step pick so that I see product judgment. | [ ] 'What I'd build next' picks one option (or a justified own idea) and says who it helps. [ ] States why it is the most valuable next step, roughly how to build it, and what to leave out. [ ] Says plainly whether it was built. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P1 | 1 | 5 | WS-OPS | 2 | US-002 | Draft
US-034 | EP-08 | F-08.2 | Late-change alert trigger (bonus, stretch) | As a staff user, I want to an alert when a builder changes a selection after revision so that I can stop costly late changes. | [ ] Given a builder change on a project in status 'revision' (Lot 15), then every staff user receives one alert with org_id = the builder org. [ ] Staff changes, and changes on projects not in revision, produce no alert; retries cannot duplicate (dedupe key = history row). [ ] Trigger function is definer, pinned search_path, not callable by authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P3 | 3 | 5 | WS-DB | 2 | US-024, US-028 | Draft
US-035 | EP-07 | F-07.3 | Pre-submission verification | As the candidate, I want to a full pre-flight so that nothing embarrassing ships. | [ ] A fresh Supabase project is rebuilt from the repo using SETUP.md only. [ ] git log -p scan finds no keys, passwords or connection strings; no service-role key anywhere; Security and Performance Advisors reviewed. [ ] CI green on main; the brief's story walked in a real browser as Ana, Mia, Bruno and Sam. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 2 | 5 | WS-OPS | 2 | US-029, US-030, US-031, US-032, US-033 | Draft
US-036 | EP-07 | F-07.3 | Submit repo, URL and two one-time secret links | As the candidate, I want to to submit exactly what was asked so that reviewers can start immediately. | [ ] Two separate one-time secret links each contain all three logins (staff, Ana, Bruno). [ ] Message contains the public repo link, live URL and both links; no password is in plain text. [ ] Supabase and Vercel stay running for 7 days after submitting. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. | P0 | 1 | 5 | WS-OPS | 2 | US-035 | Draft

## Sprint Backlog
Sprint # | Goal | Stories | Est. Points | External Dependencies | Deliverables
1 | Session 1: Foundation and data layer: repo, deploy, identity, RLS, builder schema, history trigger, seed, stall rule view, login. | US-001, US-002, US-003, US-004, US-005, US-006, US-007, US-008, US-009, US-010, US-011, US-012, US-013, US-014, US-015, US-016, US-017, US-018, US-019 | 34 | None | Live URL on Vercel, migrated and seeded database with isolation tests passing, stall views correct on seed, working login.
2 | Session 2: Screens, detector, automation proof, docs and submission. Bonus last. | US-020, US-021, US-022, US-023, US-024, US-025, US-026, US-027, US-028, US-029, US-030, US-031, US-032, US-033, US-034, US-035, US-036 | 35 | US-002, US-006, US-013, US-014, US-015, US-018, US-019 | All five screens, scheduled and manual detector with proof tests, SETUP/DESIGN/MIGRATIONS, submission package.
Total |  | 36 stories | 69 |  | Matches Product Backlog total (69).

## Technical Backlog
Task ID | Category | Task | Story | Wave | Sprint
TT-001 | Infra | Create Supabase project and run supabase link | US-004 | 1 | 1
TT-002 | Infra | Check pg_cron is available on the free project (fallback: Vercel Cron option) | US-004 | 1 | 1
TT-003 | Infra | Create Vercel project, set NEXT_PUBLIC_* vars in 3 environments | US-005 | 1 | 1
TT-004 | DevOps | GitHub Actions web job: lint, typecheck, build | US-006 | 1 | 1
TT-005 | DevOps | GitHub Actions db job: supabase start, seed, run SQL tests | US-029 | 5 | 2
TT-006 | DB | Migration: shared trigger functions | US-007 | 1 | 1
TT-007 | DB | Migration: identity tables | US-008 | 1 | 1
TT-008 | DB | Migration: auth-mirror trigger + backfill | US-009 | 1 | 1
TT-009 | DB | Migration: RLS helpers | US-010 | 1 | 1
TT-010 | DB | Migration: identity RLS | US-011 | 1 | 1
TT-011 | DB | Migration: builder core tables and composite FKs | US-012 | 2 | 1
TT-012 | DB | Migration: builder RLS and grants | US-013 | 2 | 1
TT-013 | DB | Migration: alerts table and column grant | US-014 | 2 | 1
TT-014 | DB | Migration: selection history trigger | US-015 | 2 | 1
TT-015 | DB | Migration: stall views (security_invoker re-set) | US-018 | 3 | 1
TT-016 | DB | Migration: detector tables and alerts.episode_id | US-023 | 4 | 2
TT-017 | DB | Migration: detector function with inner-block failure logging | US-024 | 4 | 2
TT-018 | DB | Migration: run-now RPC | US-025 | 4 | 2
TT-019 | DB | Migration: pg_cron schedule | US-026 | 4 | 2
TT-020 | API | Expose public and builder schemas (config.toml + hosted settings) | US-013 | 2 | 1
TT-021 | BE | Server actions: signIn, signOut | US-019 | 3 | 1
TT-022 | BE | Server actions: setSelection, clearSelection | US-021 | 3 | 2
TT-023 | BE | Server action: markAlertRead | US-022 | 3 | 2
TT-024 | BE | Server action: runDetectorNow (calls RPC) | US-027 | 4 | 2
TT-025 | FE | Pages: /login, /projects, /projects/[id], /alerts, /detector | US-020 | 3 | 2
TT-026 | Security | Audit: every table enabled+forced, every definer fn pinned and revoked | US-017 | 2 | 1
TT-027 | Security | Secret scan of git log -p; confirm no service-role key | US-035 | 5 | 2
TT-028 | Monitoring | Use stall_runs and cron.job_run_details as the run dashboard | US-027 | 4 | 2
TT-029 | Monitoring | Run Security and Performance Advisors, resolve or justify | US-035 | 5 | 2

## Architecture & Decisions
Area | Decision | Rationale | Rejected alternative
Overview | Next.js App Router on Vercel talks to Supabase Postgres and Auth as the signed-in user. All authorization lives in Postgres. | The brief says the database is the wall, not the UI or an API route. | Custom API layer with service role (rejected: bypasses RLS).
Stack | Next.js + TypeScript, Supabase (Postgres, Auth), Vercel, GitHub Actions, pg_cron. | Fixed by the brief; everything else chosen to stay boring. | Other frameworks (not allowed).
Schemas | public = identity; builder = business data, detector tables and alerts; private = RLS helpers and internal functions (not exposed). | Matches the brief's schema rules; keeps detector tables readable by /detector through RLS. | Separate unexposed schema for detector tables (needs staff RPC for reads).
Tenant guard | Every child table has org_id and a composite FK to its parent's (id, org_id). | Stops tagging a row with your own org_id while attaching it to another org's parent. | org_id-only policies (bypassable).
Authorization | Policies use org_id = any (private.current_user_org_ids()) or private.is_staff(); alerts use user_id = auth.uid(); detector tables are staff-only. | One audited predicate; narrower scopes where the brief demands. | JWT claims or user_metadata roles (forbidden).
Identity writes | No app writes to orgs, users or memberships; mirror trigger and guarded RPCs only. | Rule 5 of the schema rules. | Client-side inserts (rejected).
History | Definer trigger writes selection_history; actor_kind is computed from memberships. | Builders cannot forge history; the stall rule can trust it. | Client-supplied actor_kind (rejected).
Stall rule | Computed live in security_invoker views from selection_history, not from selections.updated_at. | Unit 7C trap: staff edits make updated_at recent. | Reading selections.updated_at (wrong).
Detector placement | pg_cron calls private.run_stall_detector(); staff Run now calls public RPC with an is_staff() check that calls the same function. | No shared secret or HTTP route; function is revoked from authenticated and anon. | Vercel Cron with CRON_SECRET hash (more moving parts; daily-only on Hobby).
De-duplication | stall_episodes unique (project_id, quiet_since); alerts only for newly inserted episodes; unique (episode_id, user_id) on alerts; advisory lock. | A time window alone is not idempotency; something must record 'done'. | Window check on last alert time (races, drifts).
Failure handling | Run row inserted outside a PL/pgSQL inner block; exception handler marks it failed with sqlerrm; inner work is rolled back automatically. | A log row in the failing transaction would vanish with it. | Raising out of the function (log rolls back).
Alerts | One row per recipient (admins of the builder org); mark-read via grant update (read_at). | RLS cannot limit columns; column grant is the guard. | Guarded RPC (also valid; more code).
Frontend | Server Components and Server Actions; @supabase/ssr; publishable key only. | Queries run as the user so RLS applies; fewer routes to secure. | Client-side fetching with custom hooks.
Environments | One Supabase project for the trial; real life = Sandbox and Production with migrations promoted by db push after Sandbox passes. | Required to be explained in SETUP.md. | Single project forever.
Observability | stall_runs (staff-readable) and cron.job_run_details; Supabase logs and Advisors. | Staff can answer 'did it run and did it work' without superuser. | External monitoring (out of scope).

## Data Model
Entity | Columns | Constraints | RLS / Access | Indexes | Delivered by
public.orgs | id, name, org_type text check (staff, builder), created_at, updated_at, lock_version | pk uuid; none to builder | forced RLS; select org-scope or staff; no app writes | - | ident
public.users | id (= auth.users.id), email, display_name, created_at, updated_at, lock_version | unique email; fk auth.users | forced RLS; select own row or staff; filled by mirror trigger | email unique | ident, mirror
public.memberships | id, user_id, org_id, role text check (admin, member), created_at, updated_at, lock_version | unique (user_id, org_id) | forced RLS; select own or org-scope; no app writes | (org_id), (user_id) | ident
builder.projects | id, org_id, name, status text check, selection_phase_started_at, selection_due_date date, archived_at, timestamps, lock_version | unique (id, org_id); check selection_phase requires started_at | select org-or-staff; update staff only with check | (org_id, status) | bcore, brls
builder.project_slots | id, org_id, project_id, room, category, timestamps, lock_version | unique (id, org_id); fk (project_id, org_id) | select org-or-staff; no writes | (project_id) | bcore, brls
builder.selections | id, org_id, slot_id, product_name, selected_by, timestamps, lock_version | unique slot_id; fk (slot_id, org_id) | select/insert/update/delete org-or-staff with check | unique (slot_id) | bcore, brls
builder.selection_history | id, org_id, slot_id, action text check (set, change, clear), product_name null, changed_by null, actor_kind text check (builder, staff), changed_at | fk (slot_id, org_id); append-only | select org-or-staff; no writes; definer trigger inserts | (slot_id, changed_at) where actor_kind = 'builder' | bcore, hist
builder.alerts | id, org_id, user_id, project_id, kind, message, read_at, episode_id, created_at, updated_at, lock_version | fk (project_id, org_id); unique (episode_id, user_id) | select/update user_id = auth.uid(); update only read_at | (user_id, created_at desc) | alerts, dtables
builder.stall_runs | id, started_at, finished_at, trigger, projects_flagged, alerts_created, status, error_message | checks on trigger and status | staff-only select; no app writes | (started_at desc) | dtables
builder.stall_episodes | id, project_id, quiet_since, created_at | unique (project_id, quiet_since) | staff-only select; no app writes | unique index | dtables
builder.v_project_stall / v_projects | project_id, org_id, org_name, name, status, quiet_since, empty_slots, is_stalled | view; security_invoker = true | inherits caller's RLS | - | view
Seed data | 3 orgs, 9 projects, slots, selections and backdated history from seed.sql; 4 test users via link-test-users.sql | load once into an empty database | triggers off during load (replica role) | - | seed
Migration order | File | Contents | Story | Sprint
01 | <timestamp>_shared_trigger_functions.sql | private schema; private.touch_updated_at() | US-007 | 1
02 | <timestamp>_identity_tables.sql | orgs, users, memberships and constraints | US-008 | 1
03 | <timestamp>_auth_mirror_trigger.sql | auth.users to public.users mirror (definer) | US-009 | 1
04 | <timestamp>_rls_helpers.sql | private.current_user_org_ids(), private.is_staff(), grants | US-010 | 1
05 | <timestamp>_identity_rls.sql | enable + force RLS, select policies, revoke app writes | US-011 | 1
06 | <timestamp>_builder_core_tables.sql | builder schema, 4 tables, composite FKs, checks, triggers | US-012 | 1
07 | <timestamp>_builder_rls_and_grants.sql | RLS, p_* policies, schema usage and table grants | US-013 | 1
08 | <timestamp>_alerts_table.sql | builder.alerts, recipient-only policies, grant update (read_at) | US-014 | 1
09 | <timestamp>_selection_history_trigger.sql | definer trigger, actor_kind, append-only guard | US-015 | 1
10 | <timestamp>_stall_views.sql | v_project_stall, v_projects (security_invoker) | US-018 | 1
11 | <timestamp>_stall_detector_tables.sql | stall_runs, stall_episodes, alerts.episode_id | US-023 | 2
12 | <timestamp>_stall_detector_function.sql | private.run_stall_detector(text), revokes | US-024 | 2
13 | <timestamp>_run_stall_detector_now_rpc.sql | public.run_stall_detector_now() staff-guarded | US-025 | 2
14 | <timestamp>_pg_cron_schedule.sql | create extension pg_cron; cron.schedule (no secrets) | US-026 | 2
15 | <timestamp>_late_change_alert.sql | OPTIONAL: trigger + dedupe for late-change alerts | US-034 | 2

## API Contracts
Endpoint | Method | Description | Request | Response | Auth | Status
/auth/v1/token?grant_type=password | POST | Sign in with email and password (Supabase Auth) | {email, password} | {access_token, refresh_token, user} | public key only | 200 / 400 invalid
Server Action signOut | ACTION | Clear session cookies | - | redirect /login | signed in | -
/rest/v1/v_projects | GET | List projects with is_stalled (Accept-Profile: builder) | query: order, filters | [{project fields, org_name, empty_slots, is_stalled}] | authenticated; RLS org-or-staff | 200
/rest/v1/project_slots?project_id=eq.{id}&select=*,selections(*) | GET | Slots with current selection (Accept-Profile: builder) | project id | [slot + selection] | authenticated; RLS | 200; empty for other org
/rest/v1/selections | POST | Set a selection | {org_id, slot_id, product_name} | created row | authenticated; with check org-or-staff; composite FK | 201 / 409 or 403 on cross-org
/rest/v1/selections?id=eq.{id} | PATCH | Change a selection | {product_name} | updated row | authenticated; RLS | 200 / 0 rows if not visible
/rest/v1/selections?id=eq.{id} | DELETE | Clear a selection (history records the clear) | - | 204 | authenticated; RLS | 204
/rest/v1/alerts?order=created_at.desc | GET | My alerts (Accept-Profile: builder) | - | [alert] | authenticated; user_id = auth.uid() | 200
/rest/v1/alerts?id=eq.{id} | PATCH | Mark alert read | {read_at} | updated row | column grant read_at only | 200 / 403 if other columns
/rest/v1/stall_runs?order=started_at.desc | GET | Run history (Accept-Profile: builder) | - | [run] | staff-only RLS | 200 (empty for non-staff)
/rest/v1/rpc/run_stall_detector_now | POST | Run the detector now | {} | stall_runs row | authenticated; body raises 42501 unless staff | 200 / 403
pg_cron job stall-detector-daily | SCHEDULE | select private.run_stall_detector('scheduled') daily | - | stall_runs row | runs as postgres; no secret | see cron.job_run_details

## QA & Testing
Feature area | Unit | Integration | E2E | Regression | UAT | Edge cases | Security cases
Identity & helpers | helper return values for member, staff, stranger | memberships + RLS end to end | - | re-run after any policy change | - | user with no membership; user in two orgs | anon calls helpers; strangers get empty
Builder RLS | policy predicates | Ana vs Builder B on 5 tables | - | catalog check in CI | - | update row into another org | cross-org insert via composite FK; forged org_id
History trigger | actor_kind logic | set/change/clear paths | - | seed still loads | - | clear writes null product; no auth.uid() | client cannot insert history
Stall rule views | greatest() with nulls | seed expectations: 3 stalled, 6 not | - | after any view re-create | - | never any selection; staff-only recent activity | security_invoker confirmed
Alerts | column grant | Ana vs Bruno vs Sam visibility | mark read as Ana | - | - | update message on own alert | staff cannot read others' alerts
Detector engine | message text, count math | first run 3/3, second run 0 | - | run on seed after every migration | - | overlapping runs; forced error | private function not callable by authenticated
Run-now RPC | - | staff succeeds, builder and anon fail | Sam clicks Run now | - | - | double click | 42501 without staff
Schedule | - | force pg_cron job once, check run log | - | - | - | job missed (state-based rule recovers) | no secret in cron command
Screens | component tests where cheap | login, list, detail, alerts, detector with seeded users | walk the brief's story in a real browser | - | reviewer walkthrough | empty states; failed run row | builder URL-hacks to Builder B project
Pipeline | - | CI db job rebuilds from migrations + seed | - | green on main | - | fresh project rebuild via SETUP.md | secret scan of git log -p

## DevOps & Deploy
Topic | Plan
Repo | Public GitHub repo; main is production; conventional commits; PRs with description (what, why, how verified); merge commit or rebase, never squash.
Branching | <type>/sw-<nnn>/<short-title>, e.g. feat/sw-024/stall-detector-function. One story per branch.
CI | GitHub Actions: web job (lint, typecheck, build) and db job (supabase start, migrations, seed, SQL tests, forced-RLS check). Red PRs are not merged.
CD | Vercel auto-deploys main to Production and every PR to a Preview. Database changes ship via supabase db push (documented in SETUP.md).
Environments | Trial: one Supabase project. Real life: Sandbox and Production Supabase projects; dev and previews use Sandbox; migrations promoted to Production only after applying cleanly to Sandbox.
Secrets | Only NEXT_PUBLIC_SUPABASE_URL and NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY (browser-safe). No service-role key anywhere. Test passwords never committed.
Monitoring & logging | stall_runs (status, error_message), cron.job_run_details, Supabase logs, Security and Performance Advisors.
Backup & DR | Trial scope: the repo is the backup (migrations + seed rebuild everything); free Supabase has limited backups. Production would use PITR on a paid plan.
Keep-alive | Free Supabase projects pause after a week idle; leave running for 7 days after submitting and unpause if asked.

## Risk Register
Risk | Impact | Probability | Mitigation | Owner
Cross-tenant leak from a missing policy or with check | High | Medium | Isolation tests (US-017) and forced-RLS catalog check in CI (US-029). | Candidate
Duplicate alerts under re-run or overlapping runs | High | Low | Episode unique key, alert unique (episode_id, user_id), advisory lock; concurrency test (US-028). | Candidate
Failure log row rolls back with the failing work | High | Medium | Inner-block pattern; failure-injection test (US-024, US-028). | Candidate
Definer function reachable by anon or public | High | Medium | Explicit revoke from public, anon (and authenticated for scheduler-only); test calls (US-028). | Candidate
Views lose security_invoker after create or replace | High | Medium | Re-set option every time; test reloptions (US-018). | Candidate
pg_cron unavailable or needs dashboard enabling | Medium | Low | Check in US-004; document dashboard step; fallback Vercel Cron with CRON_SECRET. | Candidate
Time budget overrun (6 to 8 hours) | Medium | High | Cut order: bonus, UI polish, then non-rule docs. Never RLS, idempotency, failure logging. | Candidate
Seed fails to load because of a name or constraint mismatch | Medium | Medium | Build migrations against seed column names; load seed early (US-016). | Candidate
Secret committed to git history | High | Low | gitignore, .env.example, scan before submit (US-035). | Candidate
Supabase free project pauses before review | Medium | Medium | Keep running 7 days; unpause when asked. | Candidate
AI-assistance expectations unclear | Low | Medium | Confirm policy with Reverie3D; disclose use in DESIGN.md if used. | Candidate
The .docx brief differs from the text version used here | Low | Low | Re-read the .docx before starting; update Gaps tab. | Candidate

## Future Improvements
Category | Idea
Nice-to-have | Email or Slack delivery of alerts (explicitly out of scope today).
Nice-to-have | Per-org configurable quiet threshold instead of fixed 5 days.
Scalability | Index tuning and batching the detector for thousands of projects.
Performance | Materialized snapshot of stall state if the live view gets slow.
Security | Automate the full Schema-rules checklist in CI (pgTAP) and add Advisor checks.
Reliability | Alert staff when a scheduled run fails (today it is recorded, not paged).
UX | lock_version conflict handling in the UI; Realtime alert updates.
Platform | Sandbox and Production Supabase projects with promotion pipeline.
AI | Summarise a builder's pending slots into the alert text.
Mobile | Responsive layout and push notifications.

## PM Import
Issue ID | Issue Type | Summary | Description | Epic Name | Epic Link | Priority | Story Points | Status | Labels | Sprint | Wave | Workstream | Blocked By
EP-01 | Epic | Project Foundation & Delivery Pipeline | Repo, design note, platforms, deploy and CI so every later change ships through PRs. Business value: Reviewers read git history and CI; this epic proves the habits graded in the brief. Acceptance Criteria: - [ ] Design note committed first; live URL; CI green; no secrets in git. Mapping: Epic EP-01 ¦ Phase Phase 1 Foundation ¦ Priority P0 ¦ Epic dependencies: None | Project Foundation & Delivery Pipeline |  | Highest |  | Draft | ep-01,phase-1,p0 |  | Wave 1
EP-02 | Epic | Identity, Tenancy & RLS Core | private schema, identity tables, auth mirror, RLS helpers and identity policies. Business value: Tenant isolation starts with identity; every later policy calls these helpers. Acceptance Criteria: - [ ] Helpers work for strangers (empty), RLS forced on identity tables, apps cannot write identity. Mapping: Epic EP-02 ¦ Phase Phase 1 Foundation ¦ Priority P0 ¦ Epic dependencies: EP-01 | Identity, Tenancy & RLS Core |  | Highest |  | Draft | ep-02,phase-1,p0 |  | Wave 1
EP-03 | Epic | Builder Data Model & Isolation Proof | builder schema, composite foreign keys, RLS, alerts storage, seed, test users and isolation tests. Business value: Builder A must never read or write Builder B data; the database is the wall. Acceptance Criteria: - [ ] Cross-tenant reads and writes fail in tests; seed loads unchanged. Mapping: Epic EP-03 ¦ Phase Phase 1 Foundation ¦ Priority P0 ¦ Epic dependencies: EP-02 | Builder Data Model & Isolation Proof |  | Highest |  | Draft | ep-03,phase-1,p0 |  | Wave 2
EP-04 | Epic | Selection Activity History | Append-only history written by a definer trigger with database-computed actor_kind. Business value: The stall rule needs trustworthy builder-vs-staff activity that clients cannot forge. Acceptance Criteria: - [ ] set/change/clear logged; actor_kind from membership; history append-only. Mapping: Epic EP-04 ¦ Phase Phase 1 Foundation ¦ Priority P0 ¦ Epic dependencies: EP-03 | Selection Activity History |  | Highest |  | Draft | ep-04,phase-1,p0 |  | Wave 2
EP-05 | Epic | Builder & Staff Screens | Login, projects list with live stalled badge, project detail, alerts inbox. Business value: Lets Ana, Mia, Bruno and Sam do the end-to-end story in a browser. Acceptance Criteria: - [ ] Whole brief story works in a real browser as each persona. Mapping: Epic EP-05 ¦ Phase Phase 1 Foundation ¦ Priority P0 ¦ Epic dependencies: EP-03, EP-04 | Builder & Staff Screens |  | Highest |  | Draft | ep-05,phase-1,p0 |  | Wave 3
EP-06 | Epic | Stall Detector & Alerts | Live stall rule, detector engine, run log, de-duplication, schedule, staff trigger, console and verification. Business value: The business problem: notice quiet projects and tell the right admins in the app. Acceptance Criteria: - [ ] 3 stalls on seed, zero duplicates on re-run, failures logged as failed, secured. Mapping: Epic EP-06 ¦ Phase Phase 2 Detector ¦ Priority P0 ¦ Epic dependencies: EP-03, EP-04 | Stall Detector & Alerts |  | Highest |  | Draft | ep-06,phase-2,p0 |  | Wave 3
EP-07 | Epic | Documentation, Verification & Submission | Automated DB checks in CI, migration ledger, SETUP.md, final DESIGN.md, pre-submit verification and submission. Business value: A stranger must rebuild the environment from the repo alone; submission has strict secrecy rules. Acceptance Criteria: - [ ] Fresh-project rebuild passes; checklist complete; two one-time secret links sent. Mapping: Epic EP-07 ¦ Phase Delivery ¦ Priority P0 ¦ Epic dependencies: EP-06 | Documentation, Verification & Submission |  | Highest |  | Draft | ep-07,phase-delivery,p0 |  | Wave 5
EP-08 | Epic | Part 3: What I'd Build Next | Written pick (required) and optional late-change alert build. Business value: Shows product judgment; bonus only if Parts 1 and 2 are solid. Acceptance Criteria: - [ ] Write-up covers why/how/leave out; bonus built to Part 2 standard or skipped. Mapping: Epic EP-08 ¦ Phase Phase 3 Next Step ¦ Priority P1 ¦ Epic dependencies: EP-06 | Part 3: What I'd Build Next |  | High |  | Draft | ep-08,phase-3,p1 |  | Wave 5
US-001 | Story | Send time estimate and planned submit date | As the candidate, I want to reply to Reverie3D with my time estimate and planned submit date so that they can track my progress against it. Acceptance Criteria: - [ ] Reply is sent before any build work starts and states an estimate of about 7 hours. - [ ] Reply names one specific planned submit date. - [ ] A copy of the message is kept in docs/tickets/SW-001.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-001 (SW-001) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.1 Kickoff & Design Note ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-01 | Highest | 1 | Ready | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-001,f-01-1 | SW Sprint 1 | Wave 1 | WS-OPS
US-002 | Story | Write and commit first DESIGN.md before any code | As the candidate, I want to a half-page DESIGN.md committed first so that reviewers can see decisions were made before code. Acceptance Criteria: - [ ] DESIGN.md starts with the two lines 'Candidate: <name>' and 'Hours spent: <n>'. - [ ] It has Problem, Goals/non-goals, planned data and permissions, and decisions with rejected alternatives. - [ ] Given the git log, when listing commits oldest first, then the DESIGN.md commit precedes every app and migration commit. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-002 (SW-002) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.1 Kickoff & Design Note ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-01 | Highest | 1 | Ready | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-002,f-01-1 | SW Sprint 1 | Wave 1 | WS-OPS
US-003 | Story | Scaffold repo and Next.js app with conventions | As the candidate, I want to a Next.js App Router TypeScript app with lint and typecheck scripts so that every later change is checked the same way. Acceptance Criteria: - [ ] TypeScript strict mode; npm run lint, typecheck and build all pass on the empty app. - [ ] .gitignore excludes .env* except .env.example, which lists NEXT_PUBLIC_SUPABASE_URL and NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY with a comment each and no values. - [ ] README explains local run; work is on a branch merged via PR with Conventional Commits. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-003 (SW-003) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.2 Repo & Platform Setup ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-01 | Highest | 2 | Draft | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-003,f-01-2 | SW Sprint 1 | Wave 1 | WS-OPS | US-002
US-004 | Story | Create Supabase project, link CLI, set exposed schemas in config.toml | As the candidate, I want to a linked Supabase project and a committed config.toml so that the database can be rebuilt from the repo. Acceptance Criteria: - [ ] supabase link succeeds and supabase/config.toml is committed with api schemas listing public and builder. - [ ] No schema object is created in the dashboard (settings only). - [ ] Steps taken are noted for SETUP.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-004 (SW-004) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.2 Repo & Platform Setup ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-01 | Highest | 1 | Draft | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-004,f-01-2 | SW Sprint 1 | Wave 1 | WS-OPS | US-003
US-005 | Story | Deploy hello page to Vercel with per-environment variables | As the candidate, I want to a live URL with env vars set per environment so that reviewers can open the app and previews work. Acceptance Criteria: - [ ] Live URL serves the hello page from main. - [ ] The two NEXT_PUBLIC variables exist in Production, Preview and Development; no service-role key is set anywhere. - [ ] A PR opened against main produces a Vercel preview deployment. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-005 (SW-005) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.3 Deploy & CI Pipeline ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-01 | Highest | 1 | Draft | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-005,f-01-3 | SW Sprint 1 | Wave 1 | WS-OPS | US-003,US-004
US-006 | Story | CI: lint, typecheck and build on every PR | As the candidate, I want to a GitHub Actions workflow so that a red PR is never merged. Acceptance Criteria: - [ ] Workflow runs lint, typecheck and build on pull_request and on push to main. - [ ] Given a deliberate lint error, when the PR runs, then CI fails (shown once, then reverted). - [ ] CI uses no secrets. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-006 (SW-006) ¦ Epic EP-01 Project Foundation & Delivery Pipeline ¦ Feature F-01.3 Deploy & CI Pipeline ¦ Wave 1 Foundations & Identity ¦ Workstream WS-OPS ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-01 | Highest | 1 | Draft | wave-1,ws-ops,sprint-1,ep-01,phase-1,p0,us-006,f-01-3 | SW Sprint 1 | Wave 1 | WS-OPS | US-003
US-007 | Story | Private schema and shared updated_at / lock_version trigger | As the candidate, I want to a private schema and one shared trigger function so that all mutable tables stamp updated_at and bump lock_version consistently. Acceptance Criteria: - [ ] Schema private exists and is not in the exposed API schemas. - [ ] private.touch_updated_at() sets updated_at = now() and lock_version = lock_version + 1 on update. - [ ] Migration has WHY/WHAT/ROLLBACK header and a MIGRATIONS.md row. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-007 (SW-007) ¦ Epic EP-02 Identity, Tenancy & RLS Core ¦ Feature F-02.1 Identity Schema ¦ Wave 1 Foundations & Identity ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-02 | Highest | 1 | Draft | wave-1,ws-db,sprint-1,ep-02,phase-1,p0,us-007,f-02-1 | SW Sprint 1 | Wave 1 | WS-DB | US-004
US-008 | Story | Identity tables: orgs, users, memberships | As the candidate, I want to orgs, users and memberships with strict constraints so that tenancy and staff status come from data the client cannot influence. Acceptance Criteria: - [ ] orgs.org_type is text with check in ('staff','builder'); memberships.role check in ('admin','member'). - [ ] unique (user_id, org_id) on memberships and unique email on users; uuid default gen_random_uuid() keys; created_at, updated_at, lock_version present. - [ ] public tables do not reference builder tables. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-008 (SW-008) ¦ Epic EP-02 Identity, Tenancy & RLS Core ¦ Feature F-02.1 Identity Schema ¦ Wave 1 Foundations & Identity ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-02 | Highest | 2 | Draft | wave-1,ws-db,sprint-1,ep-02,phase-1,p0,us-008,f-02-1 | SW Sprint 1 | Wave 1 | WS-DB | US-007
US-009 | Story | Auth-mirror trigger copies auth.users into public.users | As the candidate, I want to new Supabase Auth users mirrored into public.users so that link-test-users.sql can find them and the app has a users table. Acceptance Criteria: - [ ] Given a user created in the dashboard, when the insert commits, then public.users has the same id and email. - [ ] Trigger function is security definer with search_path = '' and execute revoked from public, anon and authenticated. - [ ] Existing auth users are backfilled by the migration. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-009 (SW-009) ¦ Epic EP-02 Identity, Tenancy & RLS Core ¦ Feature F-02.2 Auth Mirror & RLS Helpers ¦ Wave 1 Foundations & Identity ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-02 | Highest | 1 | Draft | wave-1,ws-db,sprint-1,ep-02,phase-1,p0,us-009,f-02-2 | SW Sprint 1 | Wave 1 | WS-DB | US-008
US-010 | Story | RLS helper functions in private | As the candidate, I want to private.current_user_org_ids() and private.is_staff() so that every policy uses one audited predicate. Acceptance Criteria: - [ ] current_user_org_ids() returns uuid[] of the caller's orgs and an empty array for a user with no membership. - [ ] is_staff() is true only for members of an org whose org_type is 'staff'. - [ ] Both are security definer, search_path = '', execute revoked from public and anon, granted to authenticated; usage on private granted; the header explains why they work despite forced RLS (postgres BYPASSRLS). Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-010 (SW-010) ¦ Epic EP-02 Identity, Tenancy & RLS Core ¦ Feature F-02.2 Auth Mirror & RLS Helpers ¦ Wave 1 Foundations & Identity ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-02 | Highest | 2 | Draft | wave-1,ws-db,sprint-1,ep-02,phase-1,p0,us-010,f-02-2 | SW Sprint 1 | Wave 1 | WS-DB | US-008
US-011 | Story | Identity RLS: enable, force, read-only policies | As a reviewer, I want to forced RLS on identity tables with read-only policies so that apps can never write orgs, memberships or users directly. Acceptance Criteria: - [ ] ENABLE and FORCE ROW LEVEL SECURITY on orgs, users, memberships with p_<table>_select policies. - [ ] INSERT, UPDATE, DELETE privileges revoked from authenticated and anon. - [ ] Given a signed-in user with no membership, when selecting from orgs, then zero rows. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-011 (SW-011) ¦ Epic EP-02 Identity, Tenancy & RLS Core ¦ Feature F-02.3 Identity RLS ¦ Wave 1 Foundations & Identity ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-02 | Highest | 2 | Draft | wave-1,ws-db,sprint-1,ep-02,phase-1,p0,us-011,f-02-3 | SW Sprint 1 | Wave 1 | WS-DB | US-010
US-012 | Story | Builder schema and core tables with composite foreign keys | As the candidate, I want to projects, slots, selections and history in schema builder so that child rows cannot disagree with their parent org. Acceptance Criteria: - [ ] Tables: projects, project_slots, selections, selection_history; statuses are text + check; unique (id, org_id) on projects and slots. - [ ] Composite FKs: slots (project_id, org_id), selections (slot_id, org_id), history (slot_id, org_id); selections.slot_id unique; history.product_name nullable. - [ ] Check: status = 'selection_phase' requires selection_phase_started_at; mutable tables carry created_at, updated_at, lock_version with the shared trigger. - [ ] Given a selection insert whose org_id differs from its slot's org_id, then a foreign key violation is raised. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-012 (SW-012) ¦ Epic EP-03 Builder Data Model & Isolation Proof ¦ Feature F-03.1 Builder Schema & RLS ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 3 |  | EP-03 | Highest | 3 | Draft | wave-2,ws-db,sprint-1,ep-03,phase-1,p0,us-012,f-03-1 | SW Sprint 1 | Wave 2 | WS-DB | US-011
US-013 | Story | Builder RLS policies, grants and API exposure | As a Builder A admin, I want to policies scoped to my org so that I can only see and change my own builder's data. Acceptance Criteria: - [ ] ENABLE and FORCE RLS on every builder table; policies named p_<table>_<command> use org_id = any (private.current_user_org_ids()) or private.is_staff(). - [ ] projects UPDATE is staff only; selections INSERT/UPDATE/DELETE use org-or-staff with check; slots and history have no write policy. - [ ] grant usage on schema builder and table grants go to authenticated only; anon has none. - [ ] builder is added to the hosted exposed schemas and recorded for SETUP.md. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-013 (SW-013) ¦ Epic EP-03 Builder Data Model & Isolation Proof ¦ Feature F-03.1 Builder Schema & RLS ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 3 |  | EP-03 | Highest | 3 | Draft | wave-2,ws-db,sprint-1,ep-03,phase-1,p0,us-013,f-03-1 | SW Sprint 1 | Wave 2 | WS-DB | US-012
US-014 | Story | Alerts table with recipient-only policies and column grant | As an admin, I want to alerts only I can read and mark read so that other users and staff cannot see my alerts. Acceptance Criteria: - [ ] builder.alerts has org_id, user_id, project_id, kind, message, read_at, created_at with composite FK (project_id, org_id). - [ ] p_alerts_select and p_alerts_update use user_id = auth.uid(); UPDATE revoked then grant update (read_at) only; no insert or delete grants to authenticated. - [ ] Given Ana updates message on her own alert, then permission denied; updating read_at succeeds. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-014 (SW-014) ¦ Epic EP-03 Builder Data Model & Isolation Proof ¦ Feature F-03.2 Alerts Storage ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-03 | Highest | 2 | Draft | wave-2,ws-db,sprint-1,ep-03,phase-1,p0,us-014,f-03-2 | SW Sprint 1 | Wave 2 | WS-DB | US-013
US-015 | Story | Selection history trigger with computed actor_kind | As a reviewer, I want to history written by a definer trigger so that builders cannot forge who made a change. Acceptance Criteria: - [ ] Insert on selections writes action 'set', update 'change', delete 'clear' (product_name null) with changed_by = auth.uid(). - [ ] actor_kind is 'builder' when the caller is a member of the project's org, else 'staff'; with no auth.uid() it is 'staff'. - [ ] Trigger function is security definer, search_path = '', execute revoked; UPDATE and DELETE on history are blocked. - [ ] Migration header says the definer use is deliberate. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-015 (SW-015) ¦ Epic EP-04 Selection Activity History ¦ Feature F-04.1 Selection History ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 3 |  | EP-04 | Highest | 3 | Draft | wave-2,ws-db,sprint-1,ep-04,phase-1,p0,us-015,f-04-1 | SW Sprint 1 | Wave 2 | WS-DB | US-013
US-016 | Story | Load seed.sql, create test users, link memberships | As the candidate, I want to provided sample data and four test users so that I can test every scenario. Acceptance Criteria: - [ ] seed.sql applies unchanged to the migrated database without error. - [ ] Users staff@stallwatch.test, ana@builder-a.test, bruno@builder-b.test, mia@builder-a.test exist and link-test-users.sql runs clean twice. - [ ] Memberships: staff admin of Reverie3D Studio, Ana admin A, Bruno admin B, Mia member A; no passwords are committed. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-016 (SW-016) ¦ Epic EP-03 Builder Data Model & Isolation Proof ¦ Feature F-03.3 Seed, Users & Isolation Proof ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 1 |  | EP-03 | Highest | 1 | Draft | wave-2,ws-db,sprint-1,ep-03,phase-1,p0,us-016,f-03-3 | SW Sprint 1 | Wave 2 | WS-DB | US-009,US-013,US-014
US-017 | Story | Isolation tests and forced-RLS catalog check | As a reviewer, I want to SQL tests that attack Builder B as Builder A so that isolation is proven, not assumed. Acceptance Criteria: - [ ] Tests in supabase/tests/ impersonate users via request.jwt.claims. - [ ] Given Ana, when selecting Builder B rows from projects, slots, selections, history and alerts, then zero rows; cross-org selection insert is rejected. - [ ] A catalog query returns zero public/builder tables lacking enable and force RLS. - [ ] Anon is denied on every table. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-017 (SW-017) ¦ Epic EP-03 Builder Data Model & Isolation Proof ¦ Feature F-03.3 Seed, Users & Isolation Proof ¦ Wave 2 Core Data + Guardrails ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-03 | Highest | 2 | Draft | wave-2,ws-db,sprint-1,ep-03,phase-1,p0,us-017,f-03-3 | SW Sprint 1 | Wave 2 | WS-DB | US-016,US-015
US-018 | Story | Stall rule views (v_project_stall, v_projects) | As a staff user, I want to a live stall rule so that the badge is always current. Acceptance Criteria: - [ ] Views are security_invoker = true (reloptions checked) and set again after any create or replace. - [ ] Given the seed, is_stalled is true for Lot 12, Unit 4B and Unit 7C and false for the other six projects. - [ ] Quiet since = greatest(selection_phase_started_at, last builder history); staff activity is ignored (Unit 7C). - [ ] Given Ana, then only Builder A rows are visible; v_projects exposes org_name, empty_slots, quiet_since, is_stalled. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-018 (SW-018) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.1 Stall Rule ¦ Wave 3 Core Value (stall rule + screens) ¦ Workstream WS-DB ¦ Sprint 1 ¦ Priority P0 ¦ Points 3 |  | EP-06 | Highest | 3 | Draft | wave-3,ws-db,sprint-1,ep-06,phase-2,p0,us-018,f-06-1 | SW Sprint 1 | Wave 3 | WS-DB | US-016,US-015
US-019 | Story | Supabase SSR clients, session refresh and /login | As a user, I want to to sign in with email and password so that I can reach my projects. Acceptance Criteria: - [ ] @supabase/ssr server and browser clients configured with the publishable key only; session refreshed in middleware/proxy. - [ ] Given valid credentials, /login redirects to /projects; invalid credentials show a plain error. - [ ] Given a signed-out visitor, /projects redirects to /login; no service-role key exists in code or Vercel. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-019 (SW-019) ¦ Epic EP-05 Builder & Staff Screens ¦ Feature F-05.1 Auth Session & Login ¦ Wave 3 Core Value (stall rule + screens) ¦ Workstream WS-WEB ¦ Sprint 1 ¦ Priority P0 ¦ Points 2 |  | EP-05 | Highest | 2 | Draft | wave-3,ws-web,sprint-1,ep-05,phase-1,p0,us-019,f-05-1 | SW Sprint 1 | Wave 3 | WS-WEB | US-005,US-016
US-020 | Story | /projects with live stalled badge | As a Builder A admin, I want to my org's projects with a stalled badge so that I know which ones need attention. Acceptance Criteria: - [ ] Builders see only their org's projects; staff see all with the org name. - [ ] Each project shows empty slots, due date and a Stalled badge driven by v_projects. - [ ] Given Ana makes one selection on Lot 12, when the page reloads, then the badge is gone. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-020 (SW-020) ¦ Epic EP-05 Builder & Staff Screens ¦ Feature F-05.2 Projects List ¦ Wave 3 Core Value (stall rule + screens) ¦ Workstream WS-WEB ¦ Sprint 2 ¦ Priority P0 ¦ Points 3 |  | EP-05 | Highest | 3 | Draft | wave-3,ws-web,sprint-2,ep-05,phase-1,p0,us-020,f-05-2 | SW Sprint 2 | Wave 3 | WS-WEB | US-018,US-019
US-021 | Story | /projects/[id] slots with set, change and clear | As a Builder A member, I want to to pick, change or clear a product per slot so that the project progresses. Acceptance Criteria: - [ ] Slots grouped by room show the current product with Set/Change and Clear. - [ ] A builder write records history with actor_kind 'builder'; a staff write records 'staff'. - [ ] Given Ana opens a Builder B project id, then not found or empty; no data leaks. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-021 (SW-021) ¦ Epic EP-05 Builder & Staff Screens ¦ Feature F-05.3 Project Detail ¦ Wave 3 Core Value (stall rule + screens) ¦ Workstream WS-WEB ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-05 | Highest | 2 | Draft | wave-3,ws-web,sprint-2,ep-05,phase-1,p0,us-021,f-05-3 | SW Sprint 2 | Wave 3 | WS-WEB | US-019,US-015
US-022 | Story | /alerts inbox with mark as read | As an admin, I want to my alerts newest first with mark as read so that I act on stalls. Acceptance Criteria: - [ ] Lists only the caller's alerts ordered by created_at desc; unread are visually distinct. - [ ] Mark as read updates read_at only. - [ ] Given Sam, then he sees only his own alerts, never Ana's. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-022 (SW-022) ¦ Epic EP-05 Builder & Staff Screens ¦ Feature F-05.4 Alerts Inbox ¦ Wave 3 Core Value (stall rule + screens) ¦ Workstream WS-WEB ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-05 | Highest | 2 | Draft | wave-3,ws-web,sprint-2,ep-05,phase-1,p0,us-022,f-05-4 | SW Sprint 2 | Wave 3 | WS-WEB | US-019,US-014
US-023 | Story | Detector tables: stall_runs, stall_episodes, alerts.episode_id | As the candidate, I want to a run log and a de-duplication record so that re-runs and overlaps cannot duplicate alerts. Acceptance Criteria: - [ ] stall_runs: started_at, finished_at, trigger in (scheduled, manual), projects_flagged, alerts_created, status in (running, succeeded, failed), error_message. - [ ] stall_episodes unique (project_id, quiet_since); alerts gets episode_id with unique (episode_id, user_id). - [ ] Both tables have forced RLS with staff-only SELECT via private.is_staff() and no write grants to authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-023 (SW-023) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.2 Detector Engine ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-06 | Highest | 2 | Draft | wave-4,ws-db,sprint-2,ep-06,phase-2,p0,us-023,f-06-2 | SW Sprint 2 | Wave 4 | WS-DB | US-013,US-014
US-024 | Story | private.run_stall_detector with failure logging and locking | As a Builder A admin, I want to an alert when my project stalls so that I act before the due date. Acceptance Criteria: - [ ] Given the seed, first run flags 3 projects and creates alerts: Ana 1, Bruno 2, Mia 0, staff 0. - [ ] Given a second immediate run, zero new episodes and zero new alerts; run still logged as succeeded. - [ ] Alert text matches: 'Lot 12 has had no builder activity for 7 days. 3 slots are still empty.' - [ ] Given a forced error inside the work block, the run row is failed with error_message and no partial alerts remain. - [ ] security definer, search_path = '', pg_advisory_xact_lock taken, execute revoked from public, anon and authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-024 (SW-024) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.2 Detector Engine ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P0 ¦ Points 5 |  | EP-06 | Highest | 5 | Draft | wave-4,ws-db,sprint-2,ep-06,phase-2,p0,us-024,f-06-2 | SW Sprint 2 | Wave 4 | WS-DB | US-023,US-018
US-025 | Story | Staff-guarded run-now RPC | As a staff user, I want to to run the detector on demand so that I can verify fixes immediately. Acceptance Criteria: - [ ] public.run_stall_detector_now() raises 42501 unless private.is_staff(); first lines of the body perform the check. - [ ] Returns the run row; revoked from public and anon, granted to authenticated. - [ ] Given Ana or anon, then forbidden; given Sam, a manual run is logged. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-025 (SW-025) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.3 Scheduling & Staff Trigger ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-06 | Highest | 2 | Draft | wave-4,ws-db,sprint-2,ep-06,phase-2,p0,us-025,f-06-3 | SW Sprint 2 | Wave 4 | WS-DB | US-024
US-026 | Story | pg_cron daily schedule | As a staff user, I want to the detector to run nightly without anyone pressing anything so that stalls are found automatically. Acceptance Criteria: - [ ] Extension pg_cron enabled; job stall-detector-daily calls private.run_stall_detector('scheduled') once a day. - [ ] The cron.schedule command contains no secret; the migration is its own file with a NOT SELF-CONTAINED note. - [ ] After forcing the job once, cron.job_run_details shows success and a scheduled stall_runs row exists. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-026 (SW-026) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.3 Scheduling & Staff Trigger ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P0 ¦ Points 1 |  | EP-06 | Highest | 1 | Draft | wave-4,ws-db,sprint-2,ep-06,phase-2,p0,us-026,f-06-3 | SW Sprint 2 | Wave 4 | WS-DB | US-024
US-027 | Story | /detector run history and Run now | As a staff user, I want to run history and a Run now button so that I can answer 'did it run and did it work?'. Acceptance Criteria: - [ ] Table lists started, finished, trigger, projects flagged, status and error, newest first; failed runs show the error. - [ ] Run now calls the RPC and refreshes with the new row. - [ ] Given Ana opens /detector, then no data and the RPC is rejected (verified in the database, not just hidden in the UI). Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-027 (SW-027) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.4 Detector Console ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-WEB ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-06 | Highest | 2 | Draft | wave-4,ws-web,sprint-2,ep-06,phase-2,p0,us-027,f-06-4 | SW Sprint 2 | Wave 4 | WS-WEB | US-025,US-019
US-028 | Story | Detector scenario tests | As a reviewer, I want to scripted scenarios so that correctness and security are proven. Acceptance Criteria: - [ ] First-run counts, immediate re-run (0 new), new stall after builder activity plus backdating (1 new alert). - [ ] Failure injection leaves a failed run with no partial alerts; two concurrent sessions create one set of alerts. - [ ] Builder, anon and direct private-function calls are rejected; staff activity on Unit 7C leaves it stalled. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-028 (SW-028) ¦ Epic EP-06 Stall Detector & Alerts ¦ Feature F-06.5 Detector Verification ¦ Wave 4 Automation (detector, schedule, console) ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P0 ¦ Points 3 |  | EP-06 | Highest | 3 | Draft | wave-4,ws-db,sprint-2,ep-06,phase-2,p0,us-028,f-06-5 | SW Sprint 2 | Wave 4 | WS-DB | US-024,US-025
US-029 | Story | CI database job | As a reviewer, I want to CI that rebuilds the DB and runs SQL tests so that regressions in security rules are caught automatically. Acceptance Criteria: - [ ] Job starts local Supabase, applies migrations, loads seed.sql, runs supabase/tests/*.sql. - [ ] Any failed assertion fails the PR; forced-RLS catalog check included. - [ ] Job is green on main. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-029 (SW-029) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.1 Automated Checks ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P1 ¦ Points 2 |  | EP-07 | High | 2 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p1,us-029,f-07-1 | SW Sprint 2 | Wave 5 | WS-OPS | US-006,US-015,US-028
US-030 | Story | MIGRATIONS.md ledger and header audit | As a reviewer, I want to one ledger row per migration and WHY/WHAT/ROLLBACK headers so that the schema history is explainable. Acceptance Criteria: - [ ] MIGRATIONS.md has one row per file with filename and what it did. - [ ] Every migration has WHY, WHAT, ROLLBACK (and NOT SELF-CONTAINED where needed) and a YYYYMMDDHHMMSS_name.sql filename. - [ ] No applied migration was edited after the fact. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-030 (SW-030) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.2 Migration & Setup Docs ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P0 ¦ Points 1 |  | EP-07 | Highest | 1 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p0,us-030,f-07-2 | SW Sprint 2 | Wave 5 | WS-OPS | US-026
US-031 | Story | SETUP.md for a teammate rebuilding from nothing | As a reviewer, I want to a literal setup guide so that I can rebuild on a fresh Supabase project. Acceptance Criteria: - [ ] Covers Supabase (create, link, db push, exposed schemas, pg_cron, other settings), order: migrations, seed, users, link script. - [ ] Covers every Vercel env var with environments and browser exposure, CI contents, and the sandbox/production split. - [ ] Followed literally on a scratch project it succeeds. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-031 (SW-031) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.2 Migration & Setup Docs ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-07 | Highest | 2 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p0,us-031,f-07-2 | SW Sprint 2 | Wave 5 | WS-OPS | US-026,US-027
US-032 | Story | Finalize DESIGN.md | As a reviewer, I want to the final design note so that I can see decisions and trade-offs. Acceptance Criteria: - [ ] Detector section states where it runs, how it gets permission, what stops duplicates, and what was given up. - [ ] 'Rules I bent' and 'What I cut' sections exist, listing any rule broken on purpose and why. - [ ] The first two lines still read Candidate and Hours spent with an honest total; the note is 1 to 2 pages. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-032 (SW-032) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.2 Migration & Setup Docs ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P0 ¦ Points 1 |  | EP-07 | Highest | 1 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p0,us-032,f-07-2 | SW Sprint 2 | Wave 5 | WS-OPS | US-031
US-033 | Story | Part 3 write-up: what I'd build next | As a reviewer, I want to a reasoned next-step pick so that I see product judgment. Acceptance Criteria: - [ ] 'What I'd build next' picks one option (or a justified own idea) and says who it helps. - [ ] States why it is the most valuable next step, roughly how to build it, and what to leave out. - [ ] Says plainly whether it was built. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-033 (SW-033) ¦ Epic EP-08 Part 3: What I'd Build Next ¦ Feature F-08.1 Next-Step Write-up ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P1 ¦ Points 1 |  | EP-08 | High | 1 | Draft | wave-5,ws-ops,sprint-2,ep-08,phase-3,p1,us-033,f-08-1 | SW Sprint 2 | Wave 5 | WS-OPS | US-002
US-034 | Story | Late-change alert trigger (bonus, stretch) | As a staff user, I want to an alert when a builder changes a selection after revision so that I can stop costly late changes. Acceptance Criteria: - [ ] Given a builder change on a project in status 'revision' (Lot 15), then every staff user receives one alert with org_id = the builder org. - [ ] Staff changes, and changes on projects not in revision, produce no alert; retries cannot duplicate (dedupe key = history row). - [ ] Trigger function is definer, pinned search_path, not callable by authenticated. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-034 (SW-034) ¦ Epic EP-08 Part 3: What I'd Build Next ¦ Feature F-08.2 Late-Change Alert (bonus) ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-DB ¦ Sprint 2 ¦ Priority P3 ¦ Points 3 |  | EP-08 | Low | 3 | Draft | wave-5,ws-db,sprint-2,ep-08,phase-3,p3,us-034,f-08-2 | SW Sprint 2 | Wave 5 | WS-DB | US-024,US-028
US-035 | Story | Pre-submission verification | As the candidate, I want to a full pre-flight so that nothing embarrassing ships. Acceptance Criteria: - [ ] A fresh Supabase project is rebuilt from the repo using SETUP.md only. - [ ] git log -p scan finds no keys, passwords or connection strings; no service-role key anywhere; Security and Performance Advisors reviewed. - [ ] CI green on main; the brief's story walked in a real browser as Ana, Mia, Bruno and Sam. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-035 (SW-035) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.3 Verification & Submission ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P0 ¦ Points 2 |  | EP-07 | Highest | 2 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p0,us-035,f-07-3 | SW Sprint 2 | Wave 5 | WS-OPS | US-029,US-030,US-031,US-032,US-033
US-036 | Story | Submit repo, URL and two one-time secret links | As the candidate, I want to to submit exactly what was asked so that reviewers can start immediately. Acceptance Criteria: - [ ] Two separate one-time secret links each contain all three logins (staff, Ana, Bruno). - [ ] Message contains the public repo link, live URL and both links; no password is in plain text. - [ ] Supabase and Vercel stay running for 7 days after submitting. Standard Done gates: tests pass, no regressions, PR reviewed (what/why/how verified) with CI green, docs updated. Mapping: Ref US-036 (SW-036) ¦ Epic EP-07 Documentation, Verification & Submission ¦ Feature F-07.3 Verification & Submission ¦ Wave 5 Docs, Part 3 & Submission ¦ Workstream WS-OPS ¦ Sprint 2 ¦ Priority P0 ¦ Points 1 |  | EP-07 | Highest | 1 | Draft | wave-5,ws-ops,sprint-2,ep-07,phase-delivery,p0,us-036,f-07-3 | SW Sprint 2 | Wave 5 | WS-OPS | US-035

## Agile & AI Practices
Area | Practice
Definition of Ready | Acceptance criteria are written and testable (Given/When/Then or checkbox).
Definition of Ready | Prerequisite stories are Done (see Blocked By).
Definition of Ready | Sized at 8 points or less (split if larger).
Definition of Ready | Security and tenant-isolation implications are noted on the story.
Definition of Ready | Migration name and header (WHY/WHAT/ROLLBACK) planned for DB stories.
Definition of Done | All acceptance criteria met and demonstrated.
Definition of Done | PR merged via merge commit or rebase (not squash); PR states what, why, how verified; CI green.
Definition of Done | Unit and integration tests pass; SQL isolation tests pass where relevant; E2E on critical paths.
Definition of Done | RLS still enabled and forced on every touched table; Advisors reviewed if schema changed.
Definition of Done | No secrets, no service-role key; docs (MIGRATIONS.md, ticket doc) updated; migrations have rollbacks.
Ceremony: Session planning (10 min) | Start of each session: pick the next stories from the sprint backlog and confirm dependencies.
Ceremony: Check-in (5 min) | Mid-session: update status, note blockers, check time against the 6-minute-per-point calibration.
Ceremony: Demo (10 min) | End of session: walk the relevant part of the brief's story in a real browser or SQL.
Ceremony: Retro (5 min) | End of Session 2: capture decisions, cuts and 'rules bent' for DESIGN.md.
AI practice: AI-assisted development | Give the agent CLAUDE.md, AGENTS.md and the story's AC; one story per branch; read every migration yourself before applying.
AI practice: AI-assisted testing | Generate SQL attack tests from the AC; run them against the real database; never trust a green test you have not seen fail.
AI practice: AI-assisted docs | Draft migration headers and SETUP.md, then rewrite WHY in your own words so it reflects real decisions.
AI practice: AI-assisted review | Second pass prompt: list tables lacking force RLS, definer functions without pinned search_path or revokes, write policies without with check.
AI practice: Policy check | Confirm whether AI assistance is acceptable for this trial and disclose it in DESIGN.md if used (see G-11).

## Gaps & Assumptions
ID | Type | Description | Impact | Recommendation / assumption taken | Blocking?
G-01 | Ambiguity | The brief's data-model table says org_type is 'staff ¦ admin', but its glossary and seed.sql use 'builder'. | Schema would reject the seed if wrong. | Assume check in ('staff','builder'). Follow the seed. | Yes (resolved)
G-02 | Ambiguity | 'Quiet for 5+ days' boundary. | Off-by-one on the day a stall begins. | Assume quiet_since <= now() - interval '5 days' (inclusive). | No
G-03 | Assumption | Who receives stall alerts. | Mia (member) and staff could otherwise get noise. | Admins of the builder org only, one alert each. | No
G-04 | Ambiguity | Meaning of 'projects flagged' in the run log. | Observability reads differently on re-runs. | projects_flagged = stalled projects seen; alerts_created = new alerts (add column). | No
G-05 | Gap | Whether builders may edit selections on projects outside selection_phase or archived. | Policy strictness vs brief silence. | Not restricted (no rule given); note in DESIGN.md as a possible tightening. | No
G-06 | Gap | Read scope of public.users. | Staff may need names later; builders should not list others. | Own row plus staff; revisit if UI needs names. | No
G-07 | NFR | No uptime, latency, RTO/RPO, retention or compliance targets are given. | None for a trial. | Free tier only; repo rebuilds the database; no retention policy. | No
G-08 | Assumption | Schedule time and timezone. | 'Overnight' is relative. | Daily at 01:00 UTC; pg_cron uses UTC. | No
G-09 | Assumption | Detector re-runs after a missed run. | Rule is state-based so catch-up is automatic. | No backfill logic needed. | No
G-10 | Assumption | Jira assigns real keys on import. | Branch and commit references (SW-nnn) could drift from blueprint numbers. | Each story keeps its blueprint number in Description and label us-nnn; SW-nnn means US-nnn. | No
G-11 | Gap | Policy on AI-assisted work for the trial is not stated. | Honesty and fairness concerns. | Confirm with Reverie3D and disclose in DESIGN.md if used; keep hours honest. | Recommended
G-12 | Assumption | The blueprint was built from the text version of the brief; the .docx was not cross-checked. | Small differences possible. | Re-read the .docx before starting. | Recommended
G-13 | Assumption | Story points calibration. | Velocity math depends on it. | 1 point is about 6 minutes; 2 sessions of about 35 points. | No
G-14 | Assumption | Session dates. | Reply must state a submit date. | Suggested: Session 1 Wed 21 Oct 2026, Session 2 Thu 22 Oct 2026, submit that evening. Adjust to your calendar. | No
G-15 | Gap | Next.js version differences (middleware vs proxy naming) are not specified. | Session refresh file name differs. | Check docs for the installed version. | No
G-16 | Gap | pg_cron enabling may require the dashboard. | Migration may fail if extension disabled. | Document in SETUP.md and migration header (NOT SELF-CONTAINED). | No
G-17 | Assumption | Marking an alert read bumps updated_at and lock_version. | Harmless side effect of the shared trigger. | Accept; trigger edits NEW, not blocked by column grant. | No
G-18 | Assumption | seed.sql loads once into an empty database. | Fixed UUIDs collide on re-load. | Use supabase db reset to start over. | No
G-19 | Assumption | Supabase key naming (publishable vs legacy anon). | Env var name. | Use NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY; works with either key value. | No
G-20 | Assumption | Alert inserts have no authenticated INSERT policy. | Looks like a missing policy to a scanner. | Inserts come only from the definer detector; explain in migration header. | No